## Slide 1: Wolfpack Study Buddies
FBLA Capstone
2023 Sample Project

## Slide 2: Overview
Tutoring program at the Idalia Elementary School
Idalia High School students tutored elementary students
Served as in-class one-on-one buddies

## Slide 3: The Why Causes and Effects Stakeholders Problem Statement Empathy and Inspiration
COVID-19
Online Learning
New Curriculum
Below benchmark students
Frustrated classroom environment
Elementary Students
  Grades 1-5
Idalia Community
  School Staff
Create a tutoring program
Team of fun and helpful tutors
Help struggling elementary students
Practice skills and build better mindsets
1-on-1 time
Teacher Relief
Reviewing skills
Good mindsets

## Slide 4: The Solution
A tutoring program
High school tutors and mentors
Relieve teacher stress
Improve knowledge and attitudes of students
Goals
Tutor 15 students
5 scholarly tutors

## Slide 5: Project Plan
Budget
Original after-school tutoring
  Snacks
  $30
Reformed in-school tutoring
  $0
No fundraising took place
Milestones
Obtain admin and parent permission
Apply tentative schedule to Week 1
Complete Week 1 with and make revisions
Complete the spring semester
Fun day with students

## Slide 6: Team Management
JULY
06
Team included:
  My mentor
  NHS Coordinator
  9 NHS Members
Organized by spreadsheet schedule

## Slide 7: Quantitative Impact

## Slide 8: Quantitative Impact
Tutored 17 kids
Team of 9 tutors
12 weeks of tutoring

## Slide 9: Qualitative Impact

## Slide 10
Lessons Learned
Scheduling tutoring times
  Matching tutor schedules to elementary schedules
Start earlier in the school year
Allow time in project schedule for roadblocks

## Slide 11: Personal and Community Growth
Personal
Communication skills
  Coordinating with teachers, tutors, and mentors
Time-management skills
  Meeting deadlines efficiently
Community
Improved school connections
Relieved teacher stress
Improved mindsets
Brought back our small community spirit

## Slide 12: Wolfpack Study Buddies
FBLA Capstone
2023 Sample Project